## Tsunamis
Tsunamis Statement of Work
| Project Title |  | Start Date
| Help Desk |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Eric (Lead), Jayce (Tester), Tre'sure (SWE), no Designer |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Eric |  |  | 2025-11-11 | 2025-12-08 | 28 |  | Not Started
| # Update README with prioritized projects | On Hold | SHA b6fa387 | 2025-11-11 | 2025-11-11 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | In Progress
| #Course Offering User Story | Complete | SHA 215af22 | 2025-11-11 | 2025-11-29 |  |  | Complete
| #GPA Calculator User Story | Complete | SHA 620f505 ,fbf1d88 ,090a8ae, c3b5e05 | 2025-11-11 | 2025-11-21 |  |  | On Hold
| #Project Maintenance (SDD, README, tests folder) | Complete | SHA 7a59184 | 2025-11-22 | 2025-12-01
| #Install & configure requests + bs4 | Complete | SHA a88abe2 | 2025-11-22 | 2025-11-29
| #Fix/organize test folder for test discovery | Complete | SHA 266c6647, a98aef9, a277a4 | 2025-11-20 | 2025-12-01
Nov 26th: 5 commits, +616, -2
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Jayce |  |  | 2025-11-20 | 2025-12-08 | 19
| # Create initial driver and Scraper class to scrape (unprocessed) academic calendar | Complete | SHA 9eaf8aa | 2025-11-20 | 2025-11-20 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
| # Create function that returns the drop dates for each semester | Complete | SHA 2b67803, d259f2b | 2025-11-21 | 2025-11-21 | 1
| #Create test for functions in PerformScraping.py | Complete | SHA 715e50c, cbcede1, 7d24d14, c449c6f, 91dc76b, 4009e4d | 2025-11-23 | 2025-11-23 | 1
| # Test resources.py | Complete | SHA ef8e7cc, 91ecc54, 1c3a8a5, 72fd372, e155579, fc7bd08 | 2025-12-01 | 2025-12-01 | 1
| #Test every resources link to ensure nothing is broken | Complete | SHA c962f98, d3153c0 | 2025-12-01 | 2025-12-01 | 1
| #Create tests for drop slip class | Complete | SHA 327df74, 721c5cd, 8d15cfc, d0b2b22, 971b233, 917d06b, | 2025-12-01 | 2025-12-01 | 1
| #Create tests for schedule class | Complete | SHA 4decf9d | 2025-12-01 | 2025-12-01 | 1 | I had more commits for this use case, but I had an issue merging the branch after the test fiolder was added.
| #Update checklist for team member contributions | Complete | SHA 7e8229d | 2025-12-01 | 2025-12-01 | 1
Nov 26th: 9 commits, +176, -15
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Complete |  | 2025-12-01 | 2025-12-01 | 1
| Tre'sure |  |  | 2025-11-12 | 2025-12-08 | 27
| # Create Course data class (strangely your data class includes 2 functions that should be in the Course class), also called in the driver | Complete | SHA e45fb67, 064665a, 62aa1ef | 2025-11-12 | 2025-11-14 | 3 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | You and Eric need to figure out why Jayce is listed as a Contributor on our shared repo but tresurent is not. Tre'sure can't earn points on this assignment unless she is a contributor to our shared repo.
| 1(a)The student types the subject in the search bar. | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3
| 1(b)The page displays a scrollable list of courses for that subject | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3
| 1(c)The student clicks on the desired course. | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3
| 1(d)The student clicks on the desired course. | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3
| 1(e)The card displays the course description, CRN, prerequisites, and the add deadline | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3
| 1(f)Implement a function that reads course data from a CSV/JSON file. | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3
| 1(g)Implement a search function that filters courses by a subject code and returns them sorted by course number. | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26
| 1(h)Implement a "view_details" function that , given a selected, prints and shows the desciption, CRN, prerequisites, and add/drop dates. | Complete | SHA 4f6dff1 | 2025-11-23 | 2025-11-26 | 3 |  |  | Nov 26th: 36 commits, +337, -250
| 1(i)Verify that entering a invalid input will show a "No courses found" message instead of ending the code. | Complete | SHA 4f6dff, ffeadef, | 2025-11-23 | 2025-11-26 | 3
| 6(a)CreAte a schedule class | Complete | SHA 8e4d561 | 2025-11-29 | 2025-11-29 | 1
| 6(b)Create a drop slip class | Complete | SHA 9ec9ea1 | 2025-11-29 | 2025-11-29 | 1
| 6(c)Create a function that writes to a drop slip file | Complete | SHA 9ec9ea1 | 2025-11-29 | 2025-11-29 | 1
| 6(d)Retrieve the CRN and all other necessary information for a course. | Complete | SHA 3e514a0 | 2025-11-29 | 2025-11-29 | 1
| 6(e)]Check if the student is registered for the course | Complete | SHA 3e514a0 | 2025-11-29 | 2025-11-29 | 1
| 6(f)The app prompts the user to enter the course that they wish to drop. | Complete | SHA 7ef6f19 | 2025-11-29 | 2025-11-29 | 1
| 4(d)Validate course code input: ensure the input is not empty and follows a pattern like SUBJECT + NUMBER. | Complete | SHA abe82b5 | 2025-11-29 | 2025-11-30 | 2
| 4(e)]Implement search function that takes the course code and checks the current semester’s course offerings. | Complete | SHA 41bb0ed | 2025-11-29 | 2025-11-30 | 2
| 4(f) Display results for offered course: show “Course is offered this semester” and list all matching sections (CRN, days/times, instructor, seats). | Complete | SHA 612067d | 2025-11-29 | 2025-11-30 | 2
| 4(g)Display message for not offered / not found course: show a clear message when no matching course exists for the semester. | Complete | SHA 612067d | 2025-11-29 | 2025-11-30 | 2
| 4(h)Handle “all sections full” case: when course is offered but has no open seats, show a message like “All sections are full.” | Complete | SHA 612067d | 2025-11-29 | 2025-11-30 | 2
| 5(b)Build a resources module with URLs, icons, and categories. | Complete | SHA 8e0ad41 | 2025-11-29 | 2025-11-30 | 2
| 5(a)Show quick-link resources so I don’t have to search XULA’s website. | Complete | SHA cd55f92 | 2025-11-29 | 2025-11-30 | 2
| 5(c)Click “Drop Deadline Calendar” and see the dates instantly. | Complete | SHA d6d3fdc | 2025-11-29 | 2025-11-30 | 2
| 5(f)Make professor office hours and emails displayed for common CPSC courses. | Complete | SHA e4b6a80 | 2025-11-29 | 2025-11-30 | 2
| 5(j)Store the resources in a JSON or CSV file so they’re easy to update later. | Complete | SHA 6a2774e | 2025-11-29 | 2025-11-30 | 2
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Vacant |  |  | 0 | 0 | 0
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL